## MOM Details
Company Name
MINUTES OF THE MEETING
Topic for the Meeting: | Daily SCRUM call
Date : | 2016-12-26
Circle: | IBU MM
Schedule Time of start: | 18:00hrs.
Actual Time of start: | 18:00hrs.
Venue: | Conference Call
Planned Duration of the Meeting: | 30 Min
Actual Duration of the Meeting : | 30 Min
AssociateName | Task | Hours | Percentage | Status
Ram | Deliverable discussion | 4 | 100 | Completed
Ram | Automation service test in VM server | 2 | 70 | Submitted
Ram | Data check for the modules | 2 | 70 | Hold
Surya Pavan | Working on Tool Testing | 3 | 90 | Inprogress
Surya Pavan | Working on Deployment of tool | 3 | 50 | Inprogress
Suresh | Working on Engine Unit testing | 6 | 70 | Submitted
Trinath Behera | Working on Jenkins and Sonar issues for Engines | 6 | 70 | Submitted